## Slide 1: Systems Analysis and Design 9th Edition
Chapter 3
Managing Systems Projects
Part 1

## Slide 2: Chapter Objectives
Explain project planning, scheduling, monitoring, and reporting
Describe work breakdown structures, task patterns, and critical path analysis
Explain techniques for estimating task completion times and costs

## Slide 3: Chapter Objectives
Describe various scheduling tools, including Gantt charts and PERT/CPM charts
Analyze task dependencies, durations, start dates, and end dates
Describe project management software and how it can assist you in project planning, estimating, scheduling, monitoring, and reporting

## Slide 4: Chapter Objectives
Discuss the importance of project risk management
Understand why projects sometimes fail

## Slide 5: Introduction
You will learn about project planning, estimating, scheduling, monitoring, reporting, and the use of project management software
You also will learn how to control and manage project changes as they occur

## Slide 6: Overview of Project Management
Project Management
A successful project must be completed on time, within budget, and deliver a quality product that satisfies users and meets requirements
Project manager or project leader
Project coordinator

## Slide 7: Overview of Project Management
What Does a Project Manager Do?
  Project manager, project leader
  Project planning
  Project scheduling
  Project monitoring and controlling
  Project reporting

## Slide 8: Overview of Project Management
Project Activities and Planning Steps

## Slide 9: Step 1: Create a Work Breakdown Structure
Work breakdown structure (WBS)
What is a Gantt Chart?
  Task group
  Can present an overview of the project’s status, but does not provide detailed information that is necessary when managing a complex project

## Slide 10: Step 1: Create a Work Breakdown Structure
What is a PERT/CPM Chart?
  The Program Evaluation Review Technique (PERT)
  Critical Path Method (CPM)
  The distinction between the two methods has disappeared over time

## Slide 11: Step 1: Create a Work Breakdown Structure
What is a PERT/CPM Chart ?
  PERT/CPM is called a bottom-up technique
  Project tasks
  Once you know the tasks, their duration, and the order in which they must be performed, you can calculate the time that it will take to complete the project

## Slide 12: Step 1: Create a Work Breakdown Structure
Which Type of Chart is Better?
  Although a Gantt chart offers a valuable snapshot view of the project, PERT charts are more useful for scheduling, monitoring, and controlling the actual work
  PERT and Gantt charts are not mutually exclusive techniques, and project managers often use both methods

## Slide 13: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Task or activity
  Event or milestone
  Break the project down into smaller tasks, creating a work breakdown structure

## Slide 14: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Listing the tasks
    Can be challenging, because the tasks might be embedded in a document
    Create a table with columns for task number, description, duration, and predecessor tasks

## Slide 15: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Estimating Task Duration
    Person-days
    Best-case estimate (B)
    Probable-case estimate (P)

## Slide 16: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Estimating Task Duration
    Worst-case estimate (W)
    Weight
(B+4P+W)
6

## Slide 17: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Factors Affecting Duration
    Project size and scope
    Human resources
    Experience with similar project
    constraints

## Slide 18: Step 1: Create a Work Breakdown Structure
Displaying the Work Breakdown Structure
  If you are managing a complex project with many tasks, you can use task groups, just as you would in a Gantt chart, to simplify the list

## Slide 19: Step 2: Identify Task Patterns
Task pattern
What are Task Patterns?
  Large or small, tasks depend on each other and must be performed in a sequence, not unlike the commands in a software program
  Task patterns can involve dependent tasks, multiple successor tasks, and multiple predecessor tasks

## Slide 20: Step 2: Identify Task Patterns
How do I Use Task Boxes to Create a Model?

## Slide 21: Step 2: Identify Task Patterns
What are the Main Types of Task Patterns?
  Dependent Tasks
  Multiple successor tasks
    Concurrent task
    Predecessor task
    Successor task
  Multiple Predecessor Tasks

## Slide 22: Step 2: Identify Task Patterns
How Do I Identify Task Patterns?
  You can identify task patterns by looking carefully at the wording of the task statement
  Words like then, when, or and are action words that signal a sequence of events
How Do I Work With Complex Task Patterns?
  When various task patterns combine, you must study the facts carefully in order to understand the logical sequence

## Slide 23: Step 2: Identify Task Patterns
How Do I Work With Complex Task Patterns?
  Consider the following three fact statements and the task patterns they represent
    Dependent tasks
    Dependent tasks and multiple successor tasks
    Dependent tasks, multiple successor tasks, and multiple predecessor tasks

## Slide 24: Step 3: Calculate the Critical Path
What Is a Critical Path?

## Slide 25: Step 3: Calculate the Critical Path
How Do I Calculate the Critical Path?
  First, you should review the task patterns
  The next step is to determine start and finish dates, which will determine the critical path for the project
  Slack time

## Slide 26: Project Monitoring and Control
Monitoring and Control Techniques
  The project manager must keep track of tasks and progress of team members, compare actual progress with the project plan, verify the completion of project milestones, and set standards and ensure that they are followed
  Structured walkthrough
  Called design reviews, code reviews, or testing reviews

## Slide 27: Project Monitoring and Control
Maintaining a Schedule
  Maintaining a project schedule can be a challenging task
  The better the original plan, the easier it will be to control the project
  If enough milestones and frequent checkpoints exist, problems will be detected rapidly
  Project managers often spend most of their time tracking the tasks along the critical path

## Slide 28: Reporting
Members of the project team regularly report their progress
Project Status Meetings

## Slide 29: Reporting
Project Status Reports
  A project manager must report regularly to his or her immediate supervisor, upper management, and users
  Should explain what you are doing to handle and monitor the problem
  Most managers recognize that problems do occur on most projects; it is better to alert management sooner rather than later

## Slide 30: Project Management Examples
PERT/CPM Example
  You construct a PERT/CPM chart from this task list in a two-step process
    Step 1: Create the work breakdown structure
    Step 2: Enter start and finish times

## Slide 31: Project Management Examples
Software-Driven Example
  Open Workbench
  Open-source software
  When you use project management software, you follow the same step-by-step process to develop a WBS and create various types of charts

## Slide 32: Project Management Examples
Software-Driven Example
  Work breakdown structure
  Gantt chart
  Network diagram
  Project planning is a dynamic task and involves constant change

## Slide 33: Risk Management
Every IT project involves risks that systems analysts and project managers must address
Risk management
Steps in Risk Management
  Develop risk management plan
  Identify the risks
    Risk identification

## Slide 34: Risk Management
Steps in Risk Management (continued)
  Analyze the risks
    Qualitative risk analysis
    Quantitative risk analysis
  Create a risk response plan
  Monitor risks

## Slide 35: Risk Management
Risk Management Software
  Most project management software includes powerful features
  The IT team can make a recommendation regarding the risks
  Depending on the nature and magnitude of the risk, the final decision might be made by management

## Slide 36: Managing for Success
Business Issues
  The major objective of every system is to provide a solution to a business problem or opportunity
  A system that falls short of business needs also produces problems for users and reduces employee morale and productivity
  Project creep

## Slide 37: Managing for Success
Budget Issues
  Cost overruns typically result from one or more of the following:
    Unrealistic estimates
    Failure to develop an accurate forecast that considers all costs over the life of the project
    Poor monitoring of progress and slow response to early warning signs of problems

## Slide 38: Managing for Success
Budget Issues
  Cost overruns typically result from one or more of the following:
    Schedule delays due to factors that were not foreseen
    Human resource issues, including turnover, inadequate training, and motivation

## Slide 39: Managing for Success
Schedule Issues
  Problems with timetables and project milestones can indicate a failure to recognize task dependencies, confusion between effort and progress, poor monitoring and control methods, personality conflicts among team members, or turnover of project personnel

## Slide 40: The Bottom Line
When problems occur, the project manager’s ability to handle the situation becomes the critical factor

## Slide 41: The Bottom Line
Sometimes, when a project experiences delays or cost overruns, the system still can be delivered on time and within budget if several less critical requirements are trimmed
Brooks’ Law

## Slide 42: Chapter Summary
Project management is the process of planning, scheduling, monitoring and controlling, and reporting upon the development of an information system
Project managers are responsible for project planning, scheduling, monitoring, and reporting
Planning, scheduling, monitoring and reporting all take place within a larger project development framework
Notes: 49

## Slide 43: Chapter Summary
In project scheduling, the project manager develops a specific time for each task, based on available resources and whether or not the task is dependent on other predecessor tasks
Every successful information system must support business requirements, stay within budget, and be available on time
Sound project management involves the same skills as any other management
Notes: 49

## Slide 44: Chapter Summary
Chapter 3 complete