## Slide 1: Systems Analysis and Design 9th Edition
Chapter 3
Managing Systems Projects
Part 2
Khayyam H. MASIYEV
BHOS
Information Security Division
Senior Lecturer
khayyam.masiyev@bhos.edu.az

## Slide 2: Course Content
  Project Management: This course provides an overview of the project environment, life-cycle and organization. It provides detailed coverage of the ten knowledge areas defined in "A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) - Project Management Institute ":
    Scope Management
    Time Management
    Cost Management
    Quality Management
    Human Resources Management
    Communications Management
    Risk Management
    Procurement Management
    Stakeholder Management
    Integration Management
  Managing Systems Projects – WBS, GanttChart, PDM, PERT, CPM

## Slide 3: References for PMP Study
This course is using following resources as references:
A Guide to The Project Management Body of Knowledge (PMBOK Guide) © PMI
PMP Exam Prep, Rita’s Course in a Book for passing the PMP Exam © Rita Mulcahy, PMP
And others (some I will share with you)

## Slide 4: PMI & PMP
The Project Management Institute (PMI) is project management professional association with over 500,000 member. Established in 1969 and located in US.
Project Management Professional (PMP) credential recognizes demonstrated knowledge and skill in leading and directing project teams and in delivering project results within the constraints of schedule, budget and resources.
PMI, PMBOK, PMP are registered marks of Project Management Institute, Inc.

## Slide 5: PMBOK Guide
Is a standard (formal document that describes established norms, methods, processes and practices)
Guidelines for managing individual projects
A good practices which are applicable to most project most of the time
A common vocabulary within project management profession
A foundational project management reference
PMI Code of Ethics and Professional Conduct is also requirement for PMP certification

## Slide 6: Advantages of Using Formal Project Management
Better control of financial, physical, and human resources
Improved customer relations
Shorter development times
Lower costs
Higher quality and increased reliability
Higher profit margins
Improved productivity
Improved productivity
Better internal coordination
Higher worker morale (less stress)

## Slide 7: What is Project?
A Project is a temporary endeavor (try) undertaken to create a unique, product, service, or result.
  Temporary = a definite beginning and end.
  A successful project must be completed on time, within budget, and deliver a quality product that satisfies users and meets requirements.

## Slide 8: Project Attributes
A project:
  Has a unique purpose
  Is temporary
  Is developed using progressive elaboration
  Requires resources, often from various areas
  Should have a primary customer or sponsor
    The project sponsor usually provides the direction and funding for the project

## Slide 9: What is Project Management?
The application of knowledge, skills, tools and technique to project activities to meet project requirements
Project Management is accomplished through the application and integration of the processes which are grouped in the 5 process groups:
  Initiating
  Planning
  Executing
  Monitoring and Controlling
  Closing
What Does a Project Manager Do?
  Project manager, project leader
  Project planning
  Project scheduling
  Project monitoring and controlling
  Project reporting

## Slide 10: Managing Project
The Project Manager is the person responsible for accomplishing the project objectives.
Managing a project includes:
  Identifying requirements.
  Establishing clear and achievable objectives.
  Balancing the competing demands of quality, scope, time and cost.
  Adapting the specifications, plans, and approach to the different concerns and expectations of the various stakeholders.

## Slide 11: Project Constraints
Every project is constrained in different ways by its:
  Scope
  Schedule/Time
  Cost/Budget
  Quality
  Resources
  Risk
If any one factor changes, at least one other factor is likely to be affected.
It is the project manager’s duty to balance these competing constraints.
COST/RESOURCES
SCHEDULE/TIME
SCOPE/QUALITY
The Triple Constraint
or
The Trade-off Triangle

## Slide 12: Project Management Framework

## Slide 13: Project Management Knowledge Areas
Four core knowledge areas lead to specific project objectives.
  Project scope management involves defining and managing all the work required to complete the project successfully.
  Project time management includes estimating how long it will take to complete the work, developing an acceptable project schedule, and ensuring timely completion of the project.
  Project cost management consists of preparing and managing the budget for the project.
  Project quality management ensures that the project will satisfy the stated or implied needs for which it was undertaken.

## Slide 14: Project Management Knowledge Areas
Four facilitating knowledge areas are the means through which the project objectives are achieved.
  Project human resource management is concerned with making effective use of the people involved with the project.
  Project communications management involves generating, collecting, disseminating, and storing project information.
  Project risk management includes identifying, analyzing, and responding to risks related to the project.
  Project procurement management involves acquiring or procuring goods and services for a project from outside the performing organization.
One knowledge area (project integration management) affects and is affected by all of the other knowledge areas.

## Slide 15: Project Management Tools and Techniques
Project management tools and techniques assist project managers and their teams in various aspects of project management.
Note that a tool or technique is more than just a software package.
Specific tools and techniques include:
    Project charters, scope statements, and WBS (scope)
    Gantt charts, network diagrams, critical path analyses (time)
    Net present value, cost estimates, and earned value management (cost)

## Slide 16: Project Success
There are different ways to define project success:
  The project met scope, time, and cost goals.
  The project satisfied the customer/sponsor.
  The project produced the desired results.

## Slide 17: Relationships Among Project Management, Program Management and Portfolio Management
  Project Management
  Program Management
  Portfolio Management
  Project Management Office
PMO
Portfolio
Program
Projects & Operation

## Slide 18: What is a Program?
A program is:
“a group of related projects managed in a coordinated way to obtain benefits and control not available from managing them individually.”
A program manager provides leadership and direction for the project managers heading the projects within the program.
ADVANTAGES
  Decreased risk

## Slide 19: Comparative Overview

## Slide 20: Stakeholders
Stakeholders are persons or organizations who are actively involved in the project or whose interests may positively or negatively affected by the performance or completion of the project.
Stakeholders have varying levels of responsibility and authority and can change over the project life cycle
Project management team must continuously identify both external and internal stakeholders
Project manager must manage the influence of various stakeholders in relation to the requirements and balance stakeholders’ interest

## Slide 21: Stakeholders
Some examples of project stakeholders

## Slide 22: Project Management Process
Enter phase/
Start project
Exit phase/
End project
Initiating
Processes
Closing
Processes
Planning
Processes
Executing
Processes
Monitoring &
Controlling Processes
Project
Boundaries

## Slide 23: Process Groups & Knowledge Areas Mapping
Knowledge Area | Process |  |  |  | 
 | Initiating | Planning | Executing | Monitoring & Control | Closing
Integration | Develop Project Charter (regulation) | Develop Project Management Plan | Direct and Manage Project Execution | Monitor and Control Project Work Perform Integrated Change Control | Close Project
Scope |  | Collect Requirements Define Scope Create WBS |  | Verify Scope Control Scope | 
Time |  | Define Activities Sequence Activities Estimate Activities Resources Estimate Activities Duration Develop Schedule |  | Control Schedule | 
Cost |  | Estimate Costs Determine Budget |  | Control Costs | 
Quality |  | Plan Quality | Perform Quality Assurance | Perform Quality Control | 
Human Resource |  | Develop Human Resources Plan | Acquire Project Team Develop Project Team Manage Project Team |  | 
Communication | Identify Stakeholders | Plan Communications | Distribute Information Manage Stakeholders Expectations | Report Performance | 
Risk |  | Plan Risk Management Identify Risk Perform Qualitative Risk Analysis Perform Quantitative Risk Analysis Plan Risk Response |  | Monitor and Control Risks | 
Procurement |  | Plan Procurements | Conduct Procurements | Administer Procurements | Close Procurements

## Slide 24: Overview of Project Management
Project Activities and Planning Steps

## Slide 25: Project Activities and Planning Steps
Step 1. Create WBS (Work Breakdown Structure)
Step 2. Identify Task Patterns
Step 3. Calculate Critical Path
Step 4. Manage the Operational Path

## Slide 26: Step 1: Create a Work Breakdown Structure
Work breakdown structure (WBS)
A work breakdown structure (WBS) involves breaking a project down into a series of smaller tasks ( components, subcomponents, activities and tasks) .
Scope – All the tasks that make up a project, no more, no less
The lowest level of the WBS – where the work is actually assigned – is called a work package

## Slide 27: WBS

## Slide 28: WBS - Levels
Level 1 – Overall Project Definition
    Highest – level entry corresponds to the overall project delivearble. E.g., Software Development Project
Level 2 – identify and define all deliverables
    Start with high-level outcomes, e.g., Create user interface
Level 3 – Decompose deliverables into high-level activities
    What needs to be done to complete the deliverable
  Level 4 – Break down activities into more granular sub-activities
      Break down to measurable level of detail
  Level 5 – As needed

## Slide 29: Beauty of the WBS
Total project can be though out in advance
Costs and budgets can be established
Responsibility assignments can begin to take shape
Can be used to begin putting together schedule
All items are potential risks. Therefore it’s essential to defining risk.

## Slide 30
Work Breakdown Structure for Computer Order Processing System Project

## Slide 31: Don’t forget
As you create the WBS, don’t try to solve the problems/risks that arise out of tasks
Have someone (more time “you”) note the risks and dependencies but don’t spend a lot of time solving the problems during WBS creation.

## Slide 32: WBS – Information It Does Not Have
Durations
    No reflection of how long things will take
Dependencies
    No causal relationships between tasks
Milestones
    Other than deliverables
So we will use Gantt Chart

## Slide 33: Step 1: Create a Work Breakdown Structure
Before creating work breakdown structures, you should understand the two primary chart types: Gantt charts and PERT/CPM charts.

## Slide 34: Step 1: Create a Work Breakdown Structure
What is a Gantt Chart?
  Task group
  Can present an overview of the project’s status, but does not provide detailed information that is necessary when managing a complex project

## Slide 35: Gantt Chart
A GANTT chart is a type of bar chart that illustrates a project schedule.
GANTT charts have become a common technique for representing the phases and activities of a project work breakdown structure.
It was introduced by Henry Gantt around 1910 – 1915.

## Slide 36: Gantt Chart

## Slide 37: Gantt Chart

## Slide 38: Gantt Chart
Characteristics:
  The bar in each row identifies the corresponding task
  The horizontal position of the bar identifies start and end times of the task
  Bar length represents the duration of the task
  Task durations can be compared easily
  Good for allocating resources and re-scheduling
  Precedence relationships can be represented using arrows
  Critical activities are usually highlighted
  Slack times are represented using bars with doted lines
  The bar of each activity begins at the activity earliest start time (ES)
  The bar of each activity ends at the activity latest finish time (LF).

## Slide 39: Gantt Chart
Advantages
  Simple
  Good visual communication to others
  Task durations can be compared easily
  Good for scheduling resources
Disadvantages
  Dependencies are more difficult to visualise
  Minor changes in data can cause major changes in the chart

## Slide 40: Precedence Diagramming Method (PDM) – a method of drawing network diagram
Precedence Diagramming Method (PDM) or Activity-on-Node (AON) – can have 4 types of dependences

## Slide 41
  EF = ES + D -1
  LS = LF – D +1
  Float (F) = LS – ES = LF – EF
  Float - Is the amount of time that a task in a project network can be delayed without causing a delay.
  ES = Early Start
  LS = Latest Start
  EF = Early Finish
  LF = Late Finish

## Slide 43: Step 1: Create a Work Breakdown Structure
What is a PERT/CPM Chart?
  The Program Evaluation Review Technique (PERT)
  Critical Path Method (CPM)

## Slide 44: Define Activities - Decomposition
Decomposition in WBS subdivide total scope of project in to smaller components and decomposition in define activities subdivide work package in to smaller, more manageable components called activities.
WBS and WBS dictionary are the basis for development of activities.

## Slide 45: 3-Points Estimate (PERT)
Also called Program Evaluation and Review technique (PERT)
Use for time and cost estimation
Expected calculated from Most-likely, Optimistic, Pessimistic (A three-point estimate uses average of optimistic, most likely, and pessimistic estimates and hence improving the accuracy.)
Range of estimate = EAD (Expected Activity Duration) +/- SD (Standard Deviation/sapma,yayinma)
 Most likely estimate (M) – The realistic and most likely estimate
 Optimistic estimate (O) is the best case scenario.
 Pessimistic estimate (P) assumes the worst case scenario
Expected (PERT Duration)
Standard
Deviation of Activity
Variance of an Activity
  Once you know the tasks, their duration, and the order in which they must be performed, you can calculate the time that it will take to complete the project

## Slide 46: HW - for your project: Tree-point estimates (PERT)
Activity | Duration |  |  | Expected Duration (PERT) | Activity Standard Deviation | Variance range | Range of the estimate
 | P | M | O |  |  |  | 
A | 3 | 5 | 1 |  |  |  | PERT +/- SD
B | 8 | 4 | 2 |  |  |  | 
C | 15 | 8 | 5 |  |  |  | 
D | 20 | 10 | 5 |  |  |  | 
Project (Total) | - |  |  |  |  |  | 

## Slide 47: Step 1: Create a Work Breakdown Structure
Which Type of Chart is Better?
  Although a Gantt chart offers a valuable snapshot view of the project, PERT charts are more useful for scheduling, monitoring, and controlling the actual work
  PERT and Gantt charts are not mutually exclusive techniques, and project managers often use both methods

## Slide 48: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Break the project down into smaller tasks, creating a work breakdown structure

## Slide 49: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Listing the tasks
    Can be challenging, because the tasks might be embedded in a document
    Create a table with columns for task number, description, duration, and predecessor tasks

## Slide 50: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Estimating Task Duration
    Person-days
    Best-case estimate (B)
    Probable-case estimate (P)

## Slide 51: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Estimating Task Duration
    Worst-case estimate (W)
    Weight
(B+4P+W)
6

## Slide 52: Step 1: Create a Work Breakdown Structure
Identifying Tasks in a Work Breakdown Structure
  Factors Affecting Duration
    Project size and scope
    Human resources
    Experience with similar project
    constraints

## Slide 53: Step 1: Create a Work Breakdown Structure
Displaying the Work Breakdown Structure
  If you are managing a complex project with many tasks, you can use task groups, just as you would in a Gantt chart, to simplify the list

## Slide 54: Step 2: Identify Task Patterns
How do I Use Task Boxes to Create a Model?

## Slide 55: Step 3: Calculate the Critical Path
What Is a Critical Path?
The critical path method calculates the early start and finish dates, and late start and finish dates for all schedule activities
Critical Path is the longest duration path
  Identify the shortest time needed to complete a project

## Slide 56: Step 3: Calculate the Critical Path
How Do I Calculate the Critical Path?
  First, you should review the task patterns
  The next step is to determine start and finish dates, which will determine the critical path for the project

## Slide 57: Project Monitoring and Control
Monitoring and Control Techniques
  The project manager must keep track of tasks and progress of team members, compare actual progress with the project plan, verify the completion of project milestones, and set standards and ensure that they are followed

## Slide 58: Reporting
Members of the project team regularly report their progress
Project Status Meetings

## Slide 59: Reporting
Project Status Reports
  A project manager must report regularly to his or her immediate supervisor, upper management, and users
  Should explain what you are doing to handle and monitor the problem
  Most managers recognize that problems do occur on most projects; it is better to alert management sooner rather than later

## Slide 60: HW - till next lecture (online lecture) day
  1. Prepare list of tasks and subtasks/ feature lists for your project
  2. Create WBS of your project
  3. Create PERT & CPM chart of your project
  Prepare and bring to the next lecture day (practice day). We will discuss through your HW.